Summer Sprint Plan

May 11 – June 30, 2026  •  51 Days

# How to Use This Plan

This plan is designed to be tough but humane. Read this section once, then return to it when you feel overwhelmed.

### The Six Tracks

- DSA — 2 hours daily, every working day. No exceptions. This is the foundation.

- MegaProject (Anisight) — Targeted blocks, due by June 7.

- MERN (concepts + projects) — Daily focus until June 20.

- AWS Certification — Daily focus until June 15 (then exam).

- Open Source — 3-4 days/week, light commitment per day.

- Communication — 30 minutes daily, every working day. Tiny dose, huge compounding effect.

### Rest Schedule (NON-NEGOTIABLE)

- Sundays = Full rest. No DSA, no projects. Recover.

- Wednesdays = Half day. DSA + one light task only. Done by 1 PM.

- This gives you ~14 recovery days across 51. That's the difference between finishing strong and burning out in week 4.

### Anti-Burnout Rules

- If you miss a day, do NOT try to make it up by doubling tomorrow. Just continue.

- Hard stop at 7:30 PM. After that, you are off duty. Phone away from study desk.

- Pomodoro inside each block: 50 min work, 10 min break. Don't grind for 2 hours straight.

- If a problem/concept blocks you for 45+ min, flag it and move on. Return tomorrow.

- Sleep 7+ hours. This is part of the plan, not optional. DSA performance dies without sleep.

### Why This Sequence

AWS exam is your earliest hard deadline (June 15), so it gets heavy weight in the first 4 weeks. MERN runs in parallel because the two complement each other (you'll deploy MERN apps to AWS). MegaProject ramps up in late May once you have foundations. DSA never stops because that's how skill is built — daily reps for 51 days.

# Track-by-Track Breakdown

## Track 1: DSA (No Leniency)

You said you're below-medium to barely-medium. Plan: build mastery by topic, not by random problem-solving. 2 hours daily, structured.

Daily structure (2 hours):

- First 30 min: Read/watch concept theory for current topic (use Striver's SDE sheet, NeetCode roadmap, or takeUforward).

- Next 75 min: Solve 2-3 problems on that topic. Start easy, end medium.

- Last 15 min: Write notes — pattern, complexity, mistake you made. This is what makes it stick.

Topic schedule across 7 weeks:

- Week 1 (May 11-17): Arrays + Strings — fundamentals, two-pointer basics

- Week 2 (May 18-24): Hashing + Sliding Window

- Week 3 (May 25-31): Stacks, Queues, Linked Lists

- Week 4 (Jun 1-7): Recursion + Backtracking (this is where most people get stuck — go slow)

- Week 5 (Jun 8-14): Trees (BT + BST traversals, problems)

- Week 6 (Jun 15-21): Dynamic Programming (1D, 2D, classic problems)

- Week 7 (Jun 22-30): Graphs (BFS, DFS, shortest path) + revision of weak topics

Weekly target: 12-15 problems solved with full understanding. Quality > quantity. Re-solving a problem from scratch the next week is more valuable than 5 new problems half-understood.

## Track 2: MegaProject (Anisight)

Deadline: June 7 (extended to June 10 buffer). Approach: ship in milestones, not in one big push.

- Week 1-2 (May 11-24): Planning, architecture, tech stack lock-in, base setup. ~1 hr/day.

- Week 3-4 (May 25-Jun 7): MAIN BUILD PHASE. ~3 hrs/day. This is when MegaProject gets your primary block.

- June 8-10: Buffer for polish, deployment, README, demo video.

Make a feature checklist on Day 1. Cross things off. Don't add scope mid-way.

## Track 3: MERN Stack

Deadline: June 20. Concepts + projects (multiple, not one giant one).

- May 11-17: MongoDB + Mongoose deep dive. Mini-project: CRUD API.

- May 18-24: Express.js + REST principles + auth (JWT). Mini-project: Auth-protected blog API.

- May 25-31: React fundamentals + hooks + state management. Mini-project: Frontend for blog API.

- Jun 1-7: React advanced (context, custom hooks, routing). Mini-project: Multi-page app.

- Jun 8-14: Full MERN integration. Mini-project: Full-stack todo or notes app with auth.

- Jun 15-20: Polish 1-2 projects to portfolio quality. Deploy them (use AWS skills here).

## Track 4: AWS Certification

Deadline: June 15. Recommended cert for first-timers: AWS Cloud Practitioner (CLF-C02). If you're aiming for Solutions Architect Associate (SAA-C03), the same plan works but problems get harder.

- Week 1-2 (May 11-24): Core services — EC2, S3, IAM, VPC basics. Watch Stephane Maarek or Adrian Cantrill course.

- Week 3 (May 25-31): Databases (RDS, DynamoDB), Lambda, networking deeper.

- Week 4 (Jun 1-7): Security, monitoring, billing, well-architected framework. Start practice tests.

- Jun 8-14: PRACTICE TESTS DAILY. Tutorials Dojo or Whizlabs. Aim for 80%+ before booking exam.

- Jun 15: Take the exam. Or earlier if you hit 85% on practice tests by Jun 12.

## Track 5: Open Source

3-4 days/week, ~1 hour each. Goal is consistent contribution, not heroic PRs.

- Pick 2-3 active beginner-friendly repos in week 1 (look for 'good first issue' label).

- Mon, Tue, Thu, Fri: 1 hour each. Read code, comment on issues, submit small PRs.

- Skip on Wednesday (half day) and weekends if tired. Don't force it.

- Realistic 7-week target: 4-8 merged PRs. Quality of contribution > number.

## Track 6: Communication & Interview Communication

30 minutes daily, weekdays only. This is the highest-ROI track for placements/interviews.

Recommended weekly curriculum:

- Monday — Read aloud (10 min) + record yourself explaining one DSA concept (20 min). Listen back.

- Tuesday — Mock behavioral question. Use STAR method. Record + review.

- Wednesday — (half day, skip if tired) Listen to one tech talk/podcast, take notes.

- Thursday — Mock technical question: explain a project or DSA solution out loud as if to interviewer.

- Friday — Vocab + filler-word audit. Practice eliminating 'um', 'like', 'basically'.

Resources: Pramp (free mock interviews — try once a week if possible), YouTube channels like Clément Mihailescu, IGotAnOffer.

# Standard Daily Templates

These are your default schedules. The week-by-week section below tells you WHAT goes into each block on each specific day.

## Standard Weekday (Mon, Tue, Thu, Fri, Sat)

| Time | Activity |
| --- | --- |
| 7:30 – 8:00 | Wake up, light exercise/walk, breakfast |
| 8:00 – 10:00 | DSA (concept + problems) — non-negotiable focus block |
| 10:00 – 10:15 | Break (walk, water, stretch — NO phone scrolling) |
| 10:15 – 12:30 | Primary deliverable (varies by phase: AWS / MERN / MegaProject) |
| 12:30 – 1:30 | Lunch + full break (rest your eyes, do not study) |
| 1:30 – 3:30 | Secondary deliverable (varies by phase) |
| 3:30 – 4:00 | Communication training (30 min daily) |
| 4:00 – 4:15 | Tea break |
| 4:15 – 6:00 | Open Source / MegaProject / Buffer time |
| 6:00 – 6:30 | Daily review: log what you did, plan tomorrow's first task |
| 6:30 – 7:30 | Light task or wrap-up if needed (optional) |
| After 7:30 | OFF. Dinner, relax, sleep by 11:00 PM |

## Half Day (Wednesday)

| Time | Activity (Half Day — recover & lock in DSA) |
| --- | --- |
| 7:30 – 8:30 | Wake up, exercise, breakfast (extra time today) |
| 8:30 – 10:30 | DSA only — review week's problems, redo 2 hard ones from memory |
| 10:30 – 11:00 | Break |
| 11:00 – 1:00 | Light task: open source PR, MERN reading, or AWS notes review |
| 1:00 onwards | OFF. Free afternoon — go out, hobby, family, rest. No guilt. |

## Rest Day (Sunday)

| Time | Activity (Full Rest Day — protect this) |
| --- | --- |
| Morning | Sleep in if you want. No alarm. Light exercise optional. |
| Anytime | OPTIONAL: 30-min weekly review (read your logs, adjust next week) |
| All day | Rest, hobby, friends, family, movies, whatever recharges you |
| Rule | ZERO DSA, ZERO project work. Brain needs to consolidate. Trust the process. |

# Week 1: May 11 – May 17

Theme: Foundations. Set up everything. DSA = Arrays/Strings. Begin AWS, MERN (Mongo), MegaProject planning.

| Date | Day | Primary Focus | Type |
| --- | --- | --- | --- |
| May 11 | Mon | DSA: Arrays intro ¦ AWS: EC2 basics ¦ MERN: MongoDB setup ¦ MegaProject: Plan v1 ¦ Comm: Read aloud ¦ OS: Find repos | FULL |
| May 12 | Tue | DSA: Two pointers ¦ AWS: EC2 hands-on ¦ MERN: Mongoose models ¦ Comm: Behavioral mock ¦ OS: First issue browse | FULL |
| May 13 | Wed | DSA: Review + redo 2 problems ¦ MERN: Light reading | HALF |
| May 14 | Thu | DSA: Prefix sum ¦ AWS: S3 + IAM ¦ MERN: CRUD API build ¦ Comm: Tech mock ¦ OS: First PR attempt | FULL |
| May 15 | Fri | DSA: Sorting basics ¦ AWS: VPC intro ¦ MERN: CRUD API finish ¦ Comm: Filler audit ¦ OS: PR follow-up | FULL |
| May 16 | Sat | DSA: Mixed problems (week recap) ¦ MegaProject: Architecture finalized ¦ MERN: Test the API | FULL |
| May 17 | Sun | REST DAY | REST |

# Week 2: May 18 – May 24

Theme: Backend depth. DSA = Hashing + Sliding Window. AWS gets denser. Express + Auth in MERN.

| Date | Day | Primary Focus | Type |
| --- | --- | --- | --- |
| May 18 | Mon | DSA: Hashing intro ¦ AWS: EC2 advanced ¦ MERN: Express setup ¦ MegaProject: Boilerplate ¦ Comm: Read aloud | FULL |
| May 19 | Tue | DSA: HashMap problems ¦ AWS: S3 advanced ¦ MERN: REST routes ¦ Comm: Behavioral mock ¦ OS: PR work | FULL |
| May 20 | Wed | DSA: Review hashing ¦ MERN: Middleware reading | HALF |
| May 21 | Thu | DSA: Sliding window ¦ AWS: IAM policies ¦ MERN: JWT auth ¦ Comm: Tech mock ¦ OS: New issue | FULL |
| May 22 | Fri | DSA: Sliding window hard ¦ AWS: VPC deep dive ¦ MERN: Auth-protected blog API ¦ Comm: Filler audit | FULL |
| May 23 | Sat | DSA: Mixed week recap ¦ MegaProject: Core feature 1 started ¦ MERN: Polish auth API | FULL |
| May 24 | Sun | REST DAY | REST |

# Week 3: May 25 – May 31

Theme: MegaProject ramp-up + Frontend begins. DSA = Stacks/Queues/LL. AWS = Databases + Lambda.

| Date | Day | Primary Focus | Type |
| --- | --- | --- | --- |
| May 25 | Mon | DSA: Stacks intro ¦ MegaProject: Build block (3hr) ¦ MERN: React fundamentals ¦ AWS: RDS ¦ Comm: Read aloud | FULL |
| May 26 | Tue | DSA: Stack problems ¦ MegaProject: Build ¦ MERN: React hooks ¦ AWS: DynamoDB ¦ OS: PR work | FULL |
| May 27 | Wed | DSA: Queues + review ¦ MegaProject: Light planning | HALF |
| May 28 | Thu | DSA: Linked List ¦ MegaProject: Build ¦ MERN: useState/useEffect ¦ AWS: Lambda ¦ Comm: Tech mock | FULL |
| May 29 | Fri | DSA: LL reverse, cycle ¦ MegaProject: Build ¦ MERN: Component patterns ¦ AWS: API Gateway ¦ Comm: Filler audit | FULL |
| May 30 | Sat | DSA: Recap ¦ MegaProject: Mid-project demo to yourself ¦ MERN: Frontend for blog API | FULL |
| May 31 | Sun | REST DAY | REST |

# Week 4: June 1 – June 7

Theme: MegaProject final push + AWS exam prep heavy. DSA = Recursion/Backtracking (the hardest topic — go slow).

| Date | Day | Primary Focus | Type |
| --- | --- | --- | --- |
| Jun 1 | Mon | DSA: Recursion basics ¦ MegaProject: 3hr build ¦ AWS: Security + monitoring ¦ MERN: React Router ¦ Comm: Read aloud | FULL |
| Jun 2 | Tue | DSA: Recursion problems ¦ MegaProject: Build ¦ AWS: Practice test #1 ¦ MERN: Context API ¦ OS: PR | FULL |
| Jun 3 | Wed | DSA: Backtracking intro ¦ MegaProject: Light polish | HALF |
| Jun 4 | Thu | DSA: Backtracking problems ¦ MegaProject: Build ¦ AWS: Practice test #2 ¦ MERN: Custom hooks ¦ Comm: Tech mock | FULL |
| Jun 5 | Fri | DSA: Backtracking hard ¦ MegaProject: FEATURE COMPLETE ¦ AWS: Well-architected ¦ MERN: Multi-page app | FULL |
| Jun 6 | Sat | DSA: Recap ¦ MegaProject: Polish + deploy + README ¦ MERN: Buffer | FULL |
| Jun 7 | Sun | REST DAY (MegaProject deadline — celebrate!) | REST |

# Week 5: June 8 – June 14

Theme: AWS exam home stretch. DSA = Trees. MERN = Full integration. MegaProject DONE — don't touch it.

| Date | Day | Primary Focus | Type |
| --- | --- | --- | --- |
| Jun 8 | Mon | DSA: Trees basics, traversals ¦ AWS: Practice test #3 ¦ MERN: Full-stack todo app ¦ Comm: Read aloud | FULL |
| Jun 9 | Tue | DSA: BT problems ¦ AWS: Practice test #4 + review wrong answers ¦ MERN: Auth integration ¦ OS: PR | FULL |
| Jun 10 | Wed | DSA: BST + review ¦ AWS: Weak-area cram | HALF |
| Jun 11 | Thu | DSA: Tree problems ¦ AWS: Practice test #5 ¦ MERN: Deployment ¦ Comm: Tech mock | FULL |
| Jun 12 | Fri | DSA: Tree hard ¦ AWS: Final practice test (target 85%) ¦ MERN: Polish ¦ Comm: Filler audit | FULL |
| Jun 13 | Sat | DSA: Light recap ¦ AWS: Light review only — REST your brain for the exam | FULL |
| Jun 14 | Sun | REST DAY (sleep early — exam tomorrow potentially) | REST |

# Week 6: June 15 – June 21

Theme: AWS exam day + post-exam recovery. DSA = DP (the second hardest topic). MERN finishes by June 20.

| Date | Day | Primary Focus | Type |
| --- | --- | --- | --- |
| Jun 15 | Mon | AWS EXAM DAY. Post-exam: light DSA only, take it easy | HALF |
| Jun 16 | Tue | DSA: DP intro ¦ MERN: Portfolio polish project 1 ¦ Comm: Behavioral mock ¦ OS: PR | FULL |
| Jun 17 | Wed | DSA: DP 1D problems ¦ MERN: Light reading | HALF |
| Jun 18 | Thu | DSA: DP classics (knapsack family) ¦ MERN: Portfolio project 2 ¦ Comm: Tech mock ¦ OS: PR | FULL |
| Jun 19 | Fri | DSA: DP 2D ¦ MERN: Final deployments ¦ Comm: Filler audit | FULL |
| Jun 20 | Sat | DSA: DP recap ¦ MERN: DEADLINE — wrap and document everything | FULL |
| Jun 21 | Sun | REST DAY | REST |

# Week 7: June 22 – June 30

Theme: Graphs + revision + portfolio polish. The home stretch. DSA only and revision of weak topics.

| Date | Day | Primary Focus | Type |
| --- | --- | --- | --- |
| Jun 22 | Mon | DSA: Graphs intro, BFS ¦ Portfolio: Update GitHub README, LinkedIn ¦ Comm: Read aloud ¦ OS: PR | FULL |
| Jun 23 | Tue | DSA: DFS, problems ¦ Portfolio: Resume update with new projects/cert ¦ Comm: Behavioral mock | FULL |
| Jun 24 | Wed | DSA: Graph problems ¦ Portfolio: Light | HALF |
| Jun 25 | Thu | DSA: Shortest path (Dijkstra basics) ¦ Revise: weak DSA topics ¦ Comm: Tech mock ¦ OS: PR | FULL |
| Jun 26 | Fri | DSA: Graph hard ¦ Revise: redo 5 hardest problems from past weeks ¦ Comm: Filler audit | FULL |
| Jun 27 | Sat | DSA: Mixed mock contest (1.5hr timed) ¦ Reflect on summer | FULL |
| Jun 28 | Sun | REST DAY | REST |
| Jun 29 | Mon | DSA: Final revision ¦ Portfolio: Final touches ¦ Mock interview if possible | FULL |
| Jun 30 | Tue | DSA: Light + summer wrap-up review ¦ CELEBRATE — you did it | FULL |

# Weekly Review Template (Sundays — Optional)

Spend 30 min Sunday morning answering these. The rest of the day is fully off.

- DSA: How many problems solved? Which topic was weakest? What pattern repeated?

- AWS / MERN / MegaProject: % progress vs plan? On track, ahead, behind?

- Communication: Did I record myself this week? What's one filler word I overuse?

- Open Source: PRs opened, merged, in review?

- Energy: Did I sleep 7+ hrs/night? Skip any rest days? (If yes, that's a problem.)

- Adjust: What ONE thing am I changing next week?

# Final Note

This plan is ambitious. Not everything will go perfectly — that's expected, not a failure. The goal is to finish June 30 with: 100+ DSA problems solved across all major topics, AWS cert in hand, a finished MegaProject, 2-3 polished MERN projects deployed, 4-8 open-source PRs merged, and noticeably better communication on camera. If you hit 75% of that, you've had a transformative summer. Trust the rest days. Show up daily. Don't grind past 7:30 PM. You've got this.